## Burn down chart
Release Burndown
Sprints completed | Expected Story Points Remaining | Actual Story Points Remaining
0 | 36 | 36
1 |  | 26
2 |  | 12
0
Sprint 1 Burndown
Sprint Days Remaining | Ideal Tasks Remaining | Actual Tasks Remaining
20 | 25 | 25
19 |  | 23
18 |  | 23
17 |  | 23
16 |  | 22
15 |  | 20
14 |  | 19
13 |  | 17
12 |  | 16
11 |  | 14
10 |  | 13
9 |  | 13
8 |  | 12
7 |  | 12
6 |  | 10
5 |  | 10
4 |  | 10
3 |  | 8
2 |  | 8
1 |  | 7
0 | 0 | 7
ALSO DO A SPRINT 2 BURNDOWN AS WELL
Sprint Days Remaining | Ideal Tasks Remaining | Actual Tasks Remaining
20 | 39 | 39
19 |  | 39
18 |  | 39
17 |  | 39
16 |  | 39
15 |  | 39
14 |  | 39
13 |  | 39
12 |  | 39
11 |  | 39
10 |  | 39
9 |  | 39
8 |  | 39
7 |  | 32
6 |  | 28
5 |  | 22
4 |  | 18
3 |  | 15
2 |  | 10
1 |  | 2
0 | 0 | 0